## Project Status Report -"MRS"
PROJECT STATUS REPORT
| Project Name : |  | "MOVIE RECOMMENDATION SYSTEM" | Team Size: |  | 7 | MENTOR MEETINGS |  | LINK | TEAM MEETINGS |  | LINK
| Project Issue Date : |  | 23-12-2023 | Project Start Date : |  | 26-12-2023
| Project Duration : |  | 4 - Weeks | Project Completion Expected Date : |  | 16-1-2024
| Project Status : |  | ON |  |  |  | Date | Topic Disscussed |  | Date | Topic Disscussed
|  |  |  | Project Status |  |  | 30/12/2023 | Discussion on Web Scrapping | https://drive.google.com/file/d/1eyUePkoHFzn_YjKay-BuJ2ZYIQh5KbH6/view?usp=drive_link | 29/12/2023 | Web scrapping issues | 26-12-2023 Meeting.png
| WEEKLY GOALS | WEEK-1 : WEB SCRAPING |  | ON |  |  | 2024-03-01 | Results of web Scrapping | https://drive.google.com/file/d/1JwoiWvDgXu7Wez2hgEkTa82fXhpfwwQ7/view?usp=drive_link | 2023-02-01 | Web Scrapping Final | https://drive.google.com/file/d/16GlpSlzys4gSgxmzRXX2bydfZDLCr41v/view?usp=drive_link
|  | WEEK-2 : EDA |  | OFF |  |  | 2024-09-01 | discussion of EDA and Vectoristaion | https://drive.google.com/file/d/1x3o_xZAZ8ieX4pZp7BiBQq7XaW2AuXGS/view?usp=drive_link | 2024-08-01 | EDA Discussion | https://drive.google.com/file/d/1oEkszxcXSe4vx5gf_FXHA1jVsIpCDxWe/view?usp=drive_link
|  | WEEK-3 : MODEL BUILDING |  | OVER |  |  | 13/1/2024 | Result of EDA & Vectorisation | https://drive.google.com/file/d/10D5ZxkpLzeJtBas6MnOUbTUUoqRTwjqf/view?usp=drive_link | 2024-11-01 | Vectorization Discussion | https://drive.google.com/file/d/1H33uoOBVW_BG8207pJl9tkuQcDcZtaRn/view?usp=drive_link
|  | WEEK-4: DEPLOYMENT |  |  |  |  | 17/1/2024 | Results of Model Building | https://drive.google.com/file/d/1dSdAPi1oLYbC7kAPq_3IoHpzABZsJqgt/view?usp=drive_link | 14/1/2024 | Model Building Discussion | https://drive.google.com/file/d/1DW8bZW_fxLfUS0uuHBChThGIEpQdZhHn/view?usp=drive_link
[7 empty] | 20/1/2024 | Final Deplyment | https://drive.google.com/file/d/17b4sR4pCa_ylh_6otpI7j3xH5X_6YJkE/view?usp=drive_link | 19/1/2024 | Final Deployment Discussion | https://drive.google.com/file/d/11pCPVHwWAxCTD6L_CwcWpxYo3uZ81vt9/view?usp=drive_link
Project Week - 1
| Project Status |  | ON
| Goals : | 1. To Learn webscrapping. |  |  | Obstacles : | 1. Data in the website was seggregated was difficult to scrape.
|  | 2. Scrapping Imdb website for max 10,000 movies. |  |  |  | 2. Url request was not responding.
|  | 3. To perform ETL. |  |  |  | 3. Only Top 100 were able to scrape.
|  | 4. To create a data set of max 10,000 movies. |  |  |  | 4 Directors and Stras inforamtion was not beeing scrapped.
| Work Accomplished | 1. Scraped 7586 movies frmIMDb. |  |  | Key Takeaways: | 1. Start with less amout of data.
|  | 2. Saving the information in the form of list. |  |  |  | 2. Tray to scrape one information at once.
|  | 3. Convert the inforamtion to data set (CSV file). |  |  |  | 3. Try to understand the HTM and CSS Document of the site.
|  | 4. Load the data set for further work. |  |  |  | 4. Always check the files for information collected.
Project Week - 2
| Project Status |  | ON
| Goals : | 1. To Perfrom EDA on the dataset. |  |  | Obstacles : | 1. Dataset was missing too many values and information.
|  | 2. To read and understand the data from dataset. |  |  |  | 2. Numerical Columns had strings in them.
|  | 3. To Map the data with the project goals. |  |  |  | 3. Due to vast dataset ploting was challenging.
|  | 4. To generate Questions and Answers for Insights. |  |  |  | 4 Directors and actors inforamtion had repeatations.
| Work Accomplished: | 1. Understood the dataset without any EDA. |  |  | Key Takeaways: | 1. Take time to read the data.
|  | 2. Performed basic EDA on the dataset. |  |  |  | 2. Try to understand data without any EDA.
|  | 3. Generated Insignts and provided Answers to Questions. |  |  |  | 3. Use different plots to understand data.
|  | 4. Plotted the data using various plots. |  |  |  | 4. Having a big data, use top contents of data to plot.
Project Week - 3
| Project Status |  | ON
| Goals : | 1. To Perform Vectorization on the contents coloum. |  |  | Obstacles : | 1. Directors and Stars coloum had multiple brackets in Tags.
|  | 2. To concatenate all the text coloums and create Tags. |  |  |  | 2. Choosing the best Techinique for Vectorization.
|  | 3. To use a perfect ML algorithm and Metric. |  |  |  | 3. Understanding similarity matrix for recommendation.
|  | 4. To build a recommendation system. |  |  |  | 4 Only index numbers were getting recommended.
| Work Accomplished: | 1. Concatenated and created a sub-data-set. |  |  | Key Takeaways: | 1. Try to understand the working behind the algorithm.
|  | 2. Created tags using all the text coloums. |  |  |  | 2. Check the similarirty score for any one of the movie.
|  | 3. Performed Vectorization on text coloum. |  |  |  | 3
|  | 4. Built a Recommendation model using cosine Similarity. |  |  |  | 4
Project Week - 4
| Project Status |  | ON
| Goals : | 1. To Deploy using Stramlit locally and Globally. |  |  | Obstacles : | 1. Poster path had errors.
|  | 2. To learn Streamlit. |  |  |  | 2. Had to learn working of API to import POSTERS.
|  | 3. To create a basic GUI for interaction. |  |  |  | 3. Unable to upload on GitHub due large file size.
|  | 4. To Import posters. |  |  |  | 4. Git-Push had many errors.
| Work Accomplished: | 1. Studied Stramlit. |  |  | Key Takeaways: | 1. Be ready to learn at any peak time.
|  | 2. Created a basic GUI and recommendation Function. |  |  |  | 2. Try to rectify the errors use web platforms.
|  | 3. Imported Posters using API's. |  |  |  | 3. Try to learn bascis and implement it first before using it on final.
|  | 4. Deployed Model on Local and Global host. |  |  |  | 4. Work on one obstacle at-a-time.